## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button)
Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name.
Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page.
Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page.
Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name.
Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.)
Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons).
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message.
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories.
Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world.
As a player, I want to move a piece so that the game progresses with the move. | Given an invalid move on the game board, when I drop the piece then it should end up on the space it started.
Given a valid move on the game board, when I drop the piece then I should be able to use the 'backup' button to undo the move made.
Given a valid move on the game board, when I drop the piece then I should be able to use the 'submit move' button to advance the game.
Given that I am not the active player, when I view my game board then I should not see any changes to the board until my opponent submits their move.
Given that I am able to make a jump move, when I make any other move then I am unable to submit it.
Given that I am in the middle of a multi-jump move, when I try to submit my move then I am unable to do so.
As a player, I want to be notified when the game is finished so that I know who won or lost. | Given that I am not the active player, when my opponent wins then I will get a message saying that I lost and to exit the game.
Given that I am not the active player, when my opponent resigns then I will get a message saying that my opponent gave up and to return to the lobby.
Given that I am the active player, when I win the game then I get a message saying that I won and to exit the game.
Given that I am the active player, when I resign from the game then I will get a message saying that I gave up and to return to the lobby.
As a player, I want to be able to forfeit a game so that I can give up and go back to the player lobby | Given that I am a player in the game, when I select the 'resign' button then I will get a message saying that I gave up and to return to the lobby.
As a player, I want to be able to spectate an active game. | Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message, granting me the option to spectate them.
Given that I am a spectator, when I try to select a piece on the board then I will be unable to select nor move it.
Given that I am a spectator, when I view the game board then I view the board from the view of the player I selected in the lobby.